## HAZID Register
HAZID — Level 3 Advisory AABs through the Seadrill Bulletin Board and the WCE Dashboard (draft 1, 22 Sep 2026)
Risk ranking columns use a placeholder 5x5 scale (Likelihood A rare to E frequent; Consequence 1 minor to 5 catastrophic) until mapped to the Seadrill matrix. Facilitator, attendees, date and MOC number to be entered in the Seadrill template.
Ref | Process step | Hazard / what could go wrong | Causes | Consequences | Existing controls (as designed) | L | C | Additional controls / actions | Action party | Residual L | Residual C | Status
H1 | Issue and distribution | AAB does not reach a rig | Flow run fails; rig contacts blank on the Rigs sheet; email lost or filtered; workbook open at run time | Rig unaware of a known equipment defect; the advisory's purpose defeated for that rig | NO RIG CONTACT branch to the office; office and gatekeeper in copy of every issue email; AAB visible on the dashboard fleet view; flow failure notification to the owner | C | 4 | Overdue chase daily until acknowledged; Rigs sheet reviewed monthly (sentinel NONE for a deliberate blank); a sent-log row per email | Dan | D | 3 | Open
H2 | Issue | Rig omitted from, or wrongly included in, the applicable list | Selection error in the tool; a new unit not yet in the rig list | Omitted rig never told; included rig acts on an advisory that does not apply | Preview before post shows rig chips; 'All rigs' and 'Clear' shortcuts; rig list held as data; dashboard shows applicable rigs per AAB; revision re-issues to the corrected list | C | 3 | Gatekeeper checks the applicable list against the equipment register (SFI) before posting; second pair of eyes in Technical Services for fleet-wide AABs | Eric | D | 3 | Open
H3 | Acknowledgement | Acknowledged but not actioned | Rig treats acknowledgement as closure; action closed without doing the work | Defect remains on the rig while the dashboard shows green | Two distinct states: acknowledged and action closed; closure requires a comment and evidence photographs; due date applies to closure; Subsea Superintendent verifies on the next rig visit | C | 4 | Dashboard shows 'acknowledged, action open' as its own colour; closure evidence reviewed by the gatekeeper; sample audit quarterly | Eric | D | 3 | Open
H4 | Revision | Rig works to a superseded revision | New revision posted; rig has printed or saved the old one | Wrong instruction followed | Revision number in the header, on the email subject and on the dashboard; a revision requiring re-acknowledgement resets every rig to outstanding; the email carries the current bulletin | C | 3 | Cover page prints 'Rev n · superseded revisions are withdrawn'; dashboard hides superseded revisions from the open list, keeps them in history | Dan | D | 2 | Open
H5 | Issue | Wrong or missing attachment | Gatekeeper attaches the wrong PDF; no PDF and the box 'no attachment' ticked in error | Rig cannot act, or acts on the wrong document | Attachment names shown in preview and on the dashboard; a primary bulletin flag; the tool refuses to post without a PDF unless explicitly ticked | D | 3 | Gatekeeper opens the preview's attachment before posting; office copy allows a same-day correction by revision | Eric | E | 2 | Open
H6 | Transport | Post fails or is truncated | Network fault; intake endpoint down; over the size limit; a file cut short in transit | AAB not filed; nobody told | Local Save always works; failed post reports HTTP status and server text and downloads the file; size guard warns at 20 MB and refuses at 30 MB; scanner lists an unparseable file on the Errors button | C | 3 | Gatekeeper confirms the AAB appears on the dashboard within 20 minutes of posting; if not, re-post from the saved file | Eric | D | 2 | Open
H7 | Acknowledgement | Rig cannot reach the dashboard server | West Gemini cannot open sacred today (route or firewall, IT ticket open); any rig with a network fault | Rig cannot acknowledge on the page | Email carries the bulletin, so the advisory still arrives; acknowledgement by reply email to the gatekeeper, entered on the rig's behalf by Technical Services with the reply on file | C | 3 | IT ticket for the West Gemini route; the acknowledgement page works from any browser on the corporate network once the route exists | Dan / IT | D | 2 | Open
H8 | Records | Loss of the AAB record or the acknowledgement history now that Maximo is not the register | SharePoint library deleted or reorganised; scanner archive script moves files; retention policy | No evidence that a rig was told or acknowledged | Posted files are never modified; SharePoint version history; scanner never archives AAB or acknowledgement files (rule to be written into Archive-ProblemFiles.ps1); server copies on sacred; dashboard data file regenerated every 10 minutes from the files | D | 4 | Retention rule for PostedReports agreed with IT (minimum the directive's retention period); quarterly export of AAB records to the Technical Services archive | Dan | E | 3 | Open
H9 | Security | Unauthorised or accidental issue of an AAB | Anyone holding the tool and the intake endpoint could post; a test post reaching the rigs | Rigs act on a false or test advisory | Endpoint is not in the tool file (gate-config.js or browser storage only); originator name and email on every record; office and gatekeeper in copy of every issue email, so a rogue post is seen the same hour; test mode sends to the office only | D | 4 | Only the gatekeeper and Dan hold the endpoint; a withdrawal revision is the correction; test mode used for every test | Eric / Dan | E | 3 | Open
H10 | Acknowledgement | Acknowledgement by the wrong person or without authority | Anyone with the page can press Acknowledge; name typed freely | Rig shown as acknowledged when the accountable role has not seen it | Name and role required; the expected role shown on the page and carried in the record; acknowledgement email to the gatekeeper names who acknowledged; Subsea Superintendent verifies on the next visit | D | 3 | Role list fixed to the decided roles; optional password gate on the page if misuse is seen | Dan | E | 2 | Open
H11 | Transition | AABs raised in both Maximo and the tool during cut-over | No cut-over date; habit | Two registers, neither complete; a Level 3 AAB missed | MOC step 7: cut-over date; open Maximo Level 3 AABs listed and re-issued or closed; directive revised before the date | C | 3 | Compliance Checklist P1 item repointed to the dashboard; Maximo Level 3 workflow disabled or marked retired | Eric | E | 2 | Open
H12 | Distribution | Notification fatigue | Too many recipients per AAB; fleet-wide AABs to all contacts | Emails ignored; a real advisory missed | One email per rig to that rig's own contacts; office in copy, not To; superintendents on their own table, not on every loop; subject line carries the AAB number and title | C | 2 | Review recipient tables quarterly; chase emails only for overdue, once a day | Dan | D | 2 | Open
H13 | Organisation | Dependence on one gatekeeper and one dashboard owner | Absence, leave, change of role | AABs not issued; dashboard not maintained | Tool file and endpoint held by two people; originator editable in the tool; all documents in the repository; training pack (item 22) | C | 3 | Named deputy for the gatekeeper role written into the directive; dashboard handover document current | Dan / Eric | D | 2 | Open
H14 | Systems | Scanner or flow stops running | Scheduled task killed, server copy failure, flow turned off, workbook renamed | No overdue chase; dashboard stale; acknowledgements not shown | Scanner writes a generated-at stamp the dashboard shows; flow failure notification to the owner; the issue email does not depend on the scanner (the flow reads the posted file directly) | C | 3 | Dashboard banner when the data is more than 2 hours old; monthly check of flow run history; scanner health on the daily task output | Dan | D | 2 | Open
H15 | Content | Advisory content wrong or unclear | Three sections written in haste; no review before post | Rig takes the wrong action | Mandatory fields: what happened, why it matters, what the rig must do; preview before post; reference documents listed; revision route for corrections | D | 3 | Second reader in Technical Services before posting a Level 3 that requires physical intervention; the directive's review rule applied | Eric | E | 2 | Open

## Legend
Likelihood
A | Rare: not expected in the life of the process
B | Unlikely: could happen once in several years
C | Possible: could happen once a year
D | Likely: expected several times a year
E | Frequent: expected monthly or more
Consequence
1 | Minor: no effect on the rig's response to the advisory
2 | Moderate: a delay of days on one rig
3 | Serious: one rig unaware of or wrong about an advisory for weeks
4 | Major: a known defect left in service on one or more rigs
5 | Catastrophic: a well control equipment failure the advisory existed to prevent
Note | Map these to the Seadrill risk matrix before the workshop; the rankings in the register are the drafter's and are to be agreed in the room.