## ORR Checklist
Seadrill
ISIT PMO
PROJECT NAME
Operational Readiness Review (ORR) Checklist
The Operational Readiness Review (ORR) is a critical step in the final phase of an IT project lifecycle, positioned between build/test completion and the formal go-live decision. It ensures all elements are in place to support the service operationally, and it acts as a gatekeeper for production deployment.
# | Acceptance Criteria | Reasonc for Criteria | Resource Support | Documentation | Applicable (Y or N) | Met (Y or N) | Risk Rating (if applicable and NOT met) | Comments
1 | Is the service owner clearly identified? | Define the application/service business owner to ensure accountability for future decisions and risks. | Business Sponsor / ISIT PM | Service Design Package (SDP), Project Handover Document
2 | Are support teams defined and aware of their roles? | Clearly define support teams to ensure clarity on ownership and responsibilities. | Service Delivery Manager | SDP, RACI, Support Model
3 | Has the Service Design Package been reviewed and accepted by all support teams? | Confirm support teams reviewed the Service Design Package (SLAs, hours, architecture, security, etc.) to enable a smooth support transition. | Service Delivery Manager, Vendors | Service Design Package (SDP)
4 | Has the Cloud Support Readiness Assessment been completed (if cloud-based)? | Complete the SIAM portal template to ensure supportability of cloud environments. | Cloud Services / SIAM | Cloud Support Readiness Assessment Template
5 | Has Early Life Support/warranty period been defined and reviewed? | Establish and review the support model during warranty to manage post-go-live risks. | Project Manager, Service Owner | Project Handover Plan, ELS Plan
6 | Have SOPs and runbooks been approved by support teams? | Ensure Service Desk, Infra, DB, and Network teams approve SOPs and runbooks to provide structured system support. | All BAU Support Teams | Support Documentation Repository, SOP Folder
7 | Have all SOPs, runbooks, and docs been updated for go-live? | Update documentation (e.g., backups, monitoring, architecture) to reflect go-live readiness. | Application Owner, Infrastructure | SOP Folder, SharePoint Support Library
8 | Are all required devices and software installed and functioning? | Verify PCs, printers, and applications are operational to enable end-user functionality. | End Device Support | Deployment Checklist, Asset Register
9 | Have users confirmed that the system works end-to-end? | Obtain user confirmation that functionality works to validate system readiness. | Business SMEs / Testers | UAT Sign-off Form, Test Summary Report
10 | Has user training been delivered, and is the process defined for new users? | Deliver training and provide materials to ensure users can operate the system effectively. | Training Lead / Business Lead | Training Records, Onboarding Guide
11 | Are workarounds for known issues documented and accepted? | Document and get business acceptance of workarounds to avoid disruption after go-live. | Application Owner, Service Desk | Known Error Log, Risk Register
12 | Are recurring system tasks automated or scheduled? | Automate or schedule backups, jobs, and reports to reduce manual errors. | Infrastructure Team | Support SOPs, System Schedule
13 | Is performance monitoring configured and understood? | Set up metrics and alerts to maintain system health and performance visibility. | Infra / Apps Monitoring Team | Monitoring Dashboard Config, SOP
14 | Are license management responsibilities defined and handed over? | Assign license responsibilities to avoid compliance issues and ensure proper usage. | Software Asset Manager | License Register, Support Handover Document
15 | Are capacity planning expectations understood by BAU teams? | Share growth projections with BAU to prepare for future scaling. | Infrastructure / App Teams | Capacity Plan, SDP
16 | Has Seadrill Security and Architecture reviewed the build? | Complete a review to ensure the build complies with security and architecture standards. | Cybersecurity, Architecture Review Board | Security Assessment Report, Architecture Review Sign-off
17 | Have SOPs for standard changes been created and added to ManageEngine? | Add standard change SOPs to ManageEngine to support smooth change execution. | Change Manager | Change SOPs, ManageEngine Config
18 | Are incident escalation and on-call details shared with the Service Desk? | Provide escalation paths and contacts to enable rapid support response. | Service Desk Lead / App Owner | Contact Matrix, Support Model
19 | Have test scripts and warranty results been shared and accepted by support? | Share results with BAU to aid future troubleshooting and understanding of system behavior. | QA / Test Manager | Test Results Summary, Transition Document
20 | Are incident priorities configured in ManageEngine? | Set incident priority levels to ensure correct response behavior. | Incident Manager | ManageEngine Configuration Log
21 | Are request types and SLAs configured in ManageEngine? | Configure SLAs and service request types to meet user support needs. | Service Desk / Request Owner | Request Catalogue, ManageEngine
22 | Is the service mapped correctly in CMDB? | Ensure CMDB mapping reflects service components and dependencies for impact analysis. | CMDB Owner / Configuration Manager | CMDB Entry, CMDB Snapshot
23 | Are ManageEngine queues for change, incident, and request setup? | Set up queues to manage ticket flow and maintain operational efficiency. | ManageEngine Admin | ManageEngine Setup Checklist
24 | Do all support teams have access and training for ManageEngine? | Provide access and training to avoid delays in ticket handling and support. | Service Delivery Manager | Training Attendance, Access Register
25 | Have service reports been configured and tested? | Set up and validate reports to track system performance and quality. | Reporting Analyst | Reporting Dashboard, Service Reports
26 | Is there a plan for replacing project-delivered equipment? | Define replacement plans to prevent downtime due to aging assets. | IT Asset Manager | Asset Lifecycle Plan, CMDB
27 | Has a system decommissioning and data retention plan been agreed? | Align on decommissioning and data retention to meet legal and compliance needs. | Data Owner / Compliance / PM | Decommission Plan, Retention Schedule
28 | Are DR procedures documented and handed over to support? | Provide DR documentation to ensure recovery from major incidents. | DR Lead / Infrastructure | DR Plan Document
29 | Has the DR plan been tested? | Test the DR plan to confirm it functions as expected during a disaster. | Infrastructure / DR Test Manager | DR Test Results Report
30 | Is there a schedule in place for future DR testing? | Define ongoing DR test schedules to maintain preparedness and up-to-date plans. | DR Coordinator | DR Test Schedule