## Summary
Argo Navis - Job Plan Gap Report (v2, after the missing job plan export)
Job plans used by open in-scope work orders (SFI 314, 331-337, 339) that are missing from a source Argo Navis needs. Fleet-wide. 13 Oct 2026, after Lee exported 52 of the missing job plans (Job plan detailed - missing plans 2026-10-13.xlsx). WO.csv is still dated 2026-09-25 (feed not refreshing). Plans on Dan's Excluded sheet are no longer counted as missing: 12 plans, 87 WOs, now deferred by default.
Missing from | Job plans | Open WOs affected | Effect in Argo Navis | Fixed by
Branch & Sequence Map | 36 | 182 | Shows as "Unassigned" - not sequenced | Dan Plant - see Branch_Map_Additions_DRAFT_for_Dan_2026-10-13.xlsx (36 proposed rows)
Job Plans and Durations | 36 | 182 | Argo Navis now uses the saved Maximo job plan duration, flagged "Maximo" | Add the reviewed duration to Job Plans and Durations.xlsm
Saved job plan workbooks | 2 | 4 | No job plan viewer, steps or parts | Export from Maximo: 0900-UR0007, 0900-UR90021 (the other 52 are now in Job Plans\)
Maximo job plan lists | 16 | 84 | "not on the job plan lists" badge (the Electrical export holds only 23 plans) | Widen the list exports (Electrical / MPD / WCE)
Checklist file (JPC REV 4) | 18 | 88 | No job plan checklist in Execute | Dan Plant - rebuild the checklist file from the next Job Plans.zip (now incl. the 52 new exports)
Any gap | 42 | 201
Excluded on Branch Map (not a gap) | 12 | 87 | Deliberately out of the BWM (in-service subsea tests, riser gantry crane...); deferred by default with a red badge | Dan's Excluded sheet - no action

## Job Plan Gaps
Job Plan | Missing From | Open WOs Affected | SFI | Description | Example Location | Discipline | Rig Count | Rigs Affected | Missing: Branch & Sequence Map | Missing: Job Plans and Durations | Missing: Saved job plan workbooks | Missing: Maximo job plan lists | Missing: Checklist file (JPC) | NOV AX issues | Materials on saved job plan | Excluded on Branch Map
0900-UB90122 | Branch Map + Durations | 14 | 331 | 12M NXT BOP BODY INSPECTION | 331.BOP1.360 | WELL CONTROL | 2 | West Jupiter; West Tellus | MISSING | MISSING | ok | ok | ok |  | none
0900-UB90129 | Branch Map + Durations | 14 | 331 | BWM RAM BLOCKS INSPECTION | 331.BOP1.314 | WELL CONTROL | 1 | West Jupiter | MISSING | MISSING | ok | ok | ok |  | none
0900-EE90061 | Branch Map + Durations + Job plan lists + Checklist | 13 | 336/337/339 | 12M GENERAL INSTRUMENTATION ELECTRICAL INSPECTION | 339.MPD1.500 | ELECTRICAL/DRILLING | 6 | West Capella; West Carina; West Gemini; West Jupiter; West Neptune; West Polaris | MISSING | MISSING | ok | MISSING | MISSING |  | none
0900-EF90051 | Branch Map + Durations + Job plan lists + Checklist | 13 | 332/337/339 | 12M MOTOR AND STARTER ELECTRICAL INSPECTION | 337.MWC3 | ELECTRICAL/DRILLING | 5 | West Carina; West Gemini; West Jupiter; West Neptune; West Vela | MISSING | MISSING | ok | MISSING | MISSING |  | none
0900-IF0003 | Branch Map + Durations + Job plan lists + Checklist | 13 | 337/339 | 12M LOCAL CONTROL PANEL INSPECTION | 339.MPD1.500 | ELECTRICAL/DRILLING | 6 | Sevan Louisiana; West Carina; West Jupiter; West Neptune; West Polaris; West Vela | MISSING | MISSING | ok | MISSING | MISSING |  | none
0900-EE5006 | Branch Map + Durations + Job plan lists + Checklist | 12 | 335 | 12M INSTRUMENTATION ELECTRICAL INSPECTION | 335.RIS1.650 | ELECTRICAL | 6 | Sonangol Quenguela; West Auriga; West Jupiter; West Saturn; West Tellus; West Vela | MISSING | MISSING | ok | MISSING | MISSING |  | none
0900-UB90125 | Branch Map + Durations | 12 | 331 | 12M POSLOCK DOOR INSPECTION | 331.BOP1.333 | WELL CONTROL | 2 | West Jupiter; West Tellus | MISSING | MISSING | ok | ok | ok |  | none
0900-RG90021 | Branch Map + Durations | 9 | 331/335 | BWM FAILSAFE VALVES INSPECTION | 331.BOP1.510 | WELL CONTROL | 1 | West Jupiter | MISSING | MISSING | ok | ok | ok |  | none
0900-UB90126 | Branch Map + Durations | 8 | 331 | BWM ULTRALOCK DOOR INSPECTION | 331.BOP1.363 | WELL CONTROL | 1 | West Jupiter | MISSING | MISSING | ok | ok | ok |  | none
0900-UC90022 | Branch Map + Durations | 8 | 331 | 12M C&K MINI CONNECTORS INSPECTION | 331.BOP1.120 | WELL CONTROL | 2 | West Jupiter; West Tellus | MISSING | MISSING | ok | ok | ok |  | none
0900-BJ0002 | Job plan lists + Checklist | 7 | 336 | 12M MUD GAS SEPARATOR INSPECTION | 336.MGS1 | DRILLING | 6 | Sonangol Libongos; Sonangol Quenguela; West Carina; West Gemini; West Polaris; West Vela | ok | ok | ok | MISSING | MISSING |  | none
0900-UB90121 | Branch Map + Durations | 7 | 331 | BWM NXT BOP BODY INSPECTION | 331.BOP1.310 | WELL CONTROL | 1 | West Jupiter | MISSING | MISSING | ok | ok | ok |  | none
0900-UB90022 | Branch Map + Durations | 6 | 331 | 12M RAM BLOCKS NDE INSPECTION | 331.BOP1.335 | WELL CONTROL | 1 | West Tellus | MISSING | MISSING | ok | ok | ok |  | none
0900-UB90124 | Branch Map + Durations | 6 | 331 | BWM POSLOCK DOOR INSPECTION | 331.BOP1.312 | WELL CONTROL | 1 | West Jupiter | MISSING | MISSING | ok | ok | ok |  | none
0900-IA5000 | Branch Map + Durations + Job plan lists + Checklist | 5 | 314/339 | 12M PLC ELECTRICAL INSPECTION | 339.MPD1.1100 | ELECTRICAL | 4 | West Capella; West Carina; West Neptune; West Saturn | MISSING | MISSING | ok | MISSING | MISSING |  | none
0900-EB5000 | Branch Map + Durations + Job plan lists + Checklist | 4 | 332 | 12M BATTERY CHARGER / UPS ELECTRICAL INSPECTION | 332.BCSS1.811 | ELECTRICAL | 2 | West Carina; West Jupiter | MISSING | MISSING | ok | MISSING | MISSING |  | none
0900-BJ0001 | Job plan lists + Checklist | 4 | 336 | 3M MUD GAS SEPARATOR INSPECTION | 336.MGS1 | DRILLING | 4 | Sonangol Libongos; West Gemini; West Polaris; West Tellus | ok | ok | ok | MISSING | MISSING |  | none
0900-UA90022 | Branch Map + Durations | 4 | 331 | 12M SBOP INSPECTION | 331.LMRP1.600 | WELL CONTROL | 2 | West Jupiter; West Tellus | MISSING | MISSING | ok | ok | ok |  | none
0900-UC90021 | Branch Map + Durations | 4 | 331 | BWM C&K MINI CONNECTORS INSPECTION | 331.BOP1.120 | WELL CONTROL | 1 | West Jupiter | MISSING | MISSING | ok | ok | ok |  | none
0900-RH90121 | Branch Map + Durations | 3 | 331 | BWM SPOOLS & BLOCKS INSPECTION | 331.BOP1.610 | WELL CONTROL | 1 | West Jupiter | MISSING | MISSING | ok | ok | ok |  | none
0900-EB5002 | Branch Map + Durations + Job plan lists + Checklist | 2 | 339 | 12M BATTERY CAPACITY/DRAW DOWN ELECTRICAL TEST | 339.MPD1.1220 | ELECTRICAL | 2 | West Auriga; West Vela | MISSING | MISSING | ok | MISSING | MISSING |  | none
0900-EB90055 | Branch Map + Durations + Job plan lists + Checklist | 2 | 332/339 | 60M UPS ELECTRICAL INSPECTION | 332.BCSS1.810 | ELECTRICAL | 2 | Sonangol Quenguela; West Carina | MISSING | MISSING | ok | MISSING | MISSING |  | none
0900-IA90061 | Branch Map + Durations + Job plan lists + Checklist | 2 | 339 | 6M INSTRUMENT (PLC / PC) CABINET INSPECTION | 339.MPD1.1230 | ELECTRICAL | 2 | West Polaris; West Vela | MISSING | MISSING | ok | MISSING | MISSING |  | none
0900-BE90024 | Branch Map + Durations | 2 | 334 | BWM DIVERTER ASSEMBLY INSPECTION | 334.DIV1.300 | WELL CONTROL | 2 | West Capella; West Tellus | MISSING | MISSING | ok | ok | ok |  | none
0900-BK5004 | Job plan lists + Checklist | 2 | 336 | 60M MUD GAS SEPARATOR | 336.MGS1 | DRILLING | 2 | Sonangol Quenguela; West Vela | ok | ok | ok | MISSING | MISSING |  | none
0900-CV8022 | Job plan lists + Checklist | 2 | 339 | 3M HYDRAULIC POWER UNIT MPD INSPECTION | 339.MPD1.1100 | MPD | 2 | West Neptune; West Tellus | ok | ok | ok | MISSING | MISSING |  | none
0900-CV90121 | Branch Map + Durations | 2 | 339 | BWM MPD UMBILICAL INSPECTION | 339.MPD1.410 | MPD | 2 | West Neptune; West Polaris | MISSING | MISSING | ok | ok | ok |  | none
0900-DP90021 | Branch Map + Durations | 2 | 335 | BWM NOV SHAFFER HYDRAULIC RISER RUNNING TOOL INSPECTION | 335.RIS1.650 | WELL CONTROL | 1 | West Tellus | MISSING | MISSING | ok | ok | ok |  | none
0900-DP90022 | Branch Map + Durations | 2 | 335 | 12M NOV SHAFFER HYDRAULIC RISER RUNNING TOOL NDT | 335.RIS1.650 | WELL CONTROL | 1 | West Tellus | MISSING | MISSING | ok | ok | ok |  | none
0900-UA90021 | Branch Map + Durations | 2 | 331 | BWM SBOP INSPECTION | 331.LMRP1.600 | WELL CONTROL | 1 | West Jupiter | MISSING | MISSING | ok | ok | ok |  | none
0900-UR0007 | Saved job plan + Checklist | 2 | 339 | BWM MPD INTEGRATED RISER JOINT SERVICE | 339.MPD1 | MPD/WELL CONTROL | 2 | West Saturn; West Vela | ok | ok | MISSING | ok | MISSING |  | none
0900-UR90021 | Saved job plan + Checklist | 2 | 339 | BWM MPD INTEGRATED RISER JOINT SERVICE | 339.MPD1.100 | MPD | 2 | West Neptune; West Polaris | ok | ok | MISSING | ok | MISSING |  | none
0900-UR90122 | Branch Map + Durations | 2 | 335 | 12M RISER ADAPTER INSPECTION | 335.RIS1.410 | WELL CONTROL | 2 | West Jupiter; West Tellus | MISSING | MISSING | ok | ok | ok |  | none
0900-CU0004 | Branch Map + Durations + Job plan lists + Checklist | 1 | 337 | 1M OXYGEN MONITOR INSPECTION | 337.MWC3 | ELECTRICAL | 1 | West Saturn | MISSING | MISSING | ok | MISSING | MISSING |  | none
0900-RR90171 | Branch Map + Durations + Job plan lists + Checklist | 1 | 336 | 12M BX TITAN VALVE MECHANICAL SERVICE | 336.CK1 | WELL CONTROL | 1 | Sonangol Quenguela | MISSING | MISSING | ok | MISSING | MISSING |  | yes
0900-XX90021 | Branch Map + Durations + Job plan lists + Checklist | 1 | 314 | OIL SAMPLING - 3.PARTY ANALYSIS ONSHORE | 314.TEN1 | WELL CONTROL | 1 | West Elara | MISSING | MISSING | ok | MISSING | MISSING |  | none
0900-BE90021 | Branch Map + Durations | 1 | 334 | BWM DIVERTER HOUSING INSPECTION | 334.DIV1.200 | WELL CONTROL | 1 | West Tellus | MISSING | MISSING | ok | ok | ok |  | none
0900-BE90022 | Branch Map + Durations | 1 | 334 | 12M DIVERTER HOUSING INSPECTION | 334.DIV1.200 | WELL CONTROL | 1 | West Tellus | MISSING | MISSING | ok | ok | ok |  | none
0900-UE90021 | Branch Map + Durations | 1 | 331 | BWM BOP MANDREL INSPECTION | 331.BOP1.110 | WELL CONTROL | 1 | West Jupiter | MISSING | MISSING | ok | ok | ok |  | none
0900-UR90121 | Branch Map + Durations | 1 | 335 | BWM RISER ADAPTER INSPECTION | 335.RIS1.410 | WELL CONTROL | 1 | West Jupiter | MISSING | MISSING | ok | ok | ok |  | none
0900-WW90021 | Branch Map + Durations | 1 | 335 | BWM NOV SHAFFER HYD. SPIDER GIMBAL AND CONTROL PANEL INSPECTION | 335.RIS1.600 | WELL CONTROL | 1 | West Tellus | MISSING | MISSING | ok | ok | ok |  | none
0900-WW90022 | Branch Map + Durations | 1 | 335 | 12M NOV SHAFFER HYD. SPIDER GIMBAL AND CONTROL PANEL INSPECTION | 335.RIS1.600 | WELL CONTROL | 1 | West Tellus | MISSING | MISSING | ok | ok | ok |  | none