## Daily Summary Report
BETWEEN WELL MAINTENANCE DAILY SUMMARY REPORT
Libongos ¦ BOP1 Offline Maintenance Plan
RIG | Libongos |  | DATA DATE |  | 2026-Oct-14 @1800 Hrs
PROJECT LOCATION | Angola |  | SYNERGY CASE NUM |  | #1870087
RIG MANAGER | Lucas Leal |  | 3rd Party Verifier |  | NA
Asst. RIG MANAGER | Geronimo Neto |  | PROJECT PLANNER |  | Brent Sherman
OIM | Ranko Karleausa |  | PROJECT LEAD |  | NA
TSL | Adam Ganesh |  | TECHNICAL SUPT. |  | Paulo Vitor
DSL | Chris Taylor |  | PROJECT TYPE |  | Offline Maintenance Plan
SUBSEA SUPERVISOR | Shay Stephens |  | ORIGINAL EST. FINISH |  | 2026-Oct-30
MAINT. ACTUAL START | 2026-Sep-30 |  | CURRENT EST. FINISH |  | 2026-Nov-03
MAINTENANCE DAY 12 of 30 | 720 hrs ¦ 30.0 days |  | PLAN VARIANCE (Days) (+ =AHEAD, - = BEHIND) |  | -111.8 Hrs
BOP NEED DATE | NA |  | TOTAL FLOAT, BOP Need |  | NA
CRITICAL PATH, SIMOPS, PROJECT PERCENTAGE
Critical Path
SIMOPS | 40.88% Complete
Project Percentage | MILESTONES
MILESTONES
BASELINE DATE | ESTIMATED DATE | ACTUAL DATE |  | MILESTONE (DESCRIPTION)
2026-Oct-17 | 2026-Oct-18 |  |  | BOP1 Lower Stack Scope Complete
2026-Oct-19 | 2026-Oct-23 |  |  | LMRP Scope Complete
2026-Oct-30 | 2026-Nov-03 |  |  | BOP1 Controls Scope Complete
2026-Oct-30 | 2026-Nov-03 |  |  | BOP1 Maintenance Complete
SCHEDULE CHANGES - BREAK-IN WORK OR DELAYS SINCE LAST REPORT
TASK ID | TASK DESCRIPTION / COMMENT
NA | NA
NA | NA
QUALITY / RIG RELIABILITY - (MATERIALS, PEOPLE, PARTS, TOOLS, ETC.)
ACTION OWNER | ESTIMATED DATE |  | DESCRIPTION / COMMENT
NA | NA |  | NA
NA | NA |  | NA
LESSONS LEARNED SINCE LAST REPORT
TASK ID | TASK DESCRIPTION / COMMENT
NA | NA
NA | NA
SCOPE CHANGE REQUEST
REQUESTED BY | TASK DESCRIPTION |  | STATUS OF REQUEST
NA | NA |  | NA
NA | NA |  | NA
PREVIOUS REPORT CYCLE – TO PRESENT
TASK ID | TASK DESCRIPTION |  |  |  | COMMENTS
A1280 | BWM BLIND SHEAR RAM DOOR INSPECTION |  |  |  | 100%
A1370 | BWM CASING SHEAR RAM DOOR INSPECTION |  |  |  | 100%
A1380 | BWM CASING SHEAR RAM DOOR INSPECTION |  |  |  | 100%
A1450 | BWM BLIND SHEAR RAM DOOR INSPECTION |  |  |  | 100%
A1460 | BWM BLIND SHEAR RAM DOOR INSPECTION |  |  |  | 100%
A1550 | BWM PIPE AND TEST RAM DOOR INSPECTION |  |  |  | 100%
A1560 | BWM PIPE AND TEST RAM DOOR INSPECTION |  |  |  | 100%
A1600 | 12M PIPE RAM BLOCK INSPECTION |  |  |  | 100%
A1610 | 12M PIPE RAM BLOCK INSPECTION |  |  |  | 100%
A1630 | BWM PIPE AND TEST RAM DOOR INSPECTION |  |  |  | 100%
A1640 | BWM PIPE AND TEST RAM DOOR INSPECTION |  |  |  | 100%
A1680 | 12M PIPE RAM BLOCK INSPECTION |  |  |  | 100%
A1690 | 12M PIPE RAM BLOCK INSPECTION |  |  |  | 100%
A1700 | BWM PIPE AND TEST RAMS |  |  |  | 75%
A1710 | BWM PIPE AND TEST RAM DOOR INSPECTION |  |  |  | 75%
A1720 | BWM PIPE AND TEST RAM DOOR INSPECTION |  |  |  | 75%
A1760 | 12M PIPE RAM BLOCK INSPECTION |  |  |  | 100%
A1770 | 12M PIPE RAM BLOCK INSPECTION |  |  |  | 100%
PROJECTED FOR NEXT REPORT CYCLE – TO PRESENT
TASK ID | TASK DESCRIPTION |  |  |  | COMMENTS
A1260 | BWM BLIND SHEAR RAM |  |  |  | 75%
A1820 | BWM HYDRAULIC SPRING ASSIST HB GATE VALVES INSPECTION |  |  |  | 75%
A1820 | BWM HYDRAULIC SPRING ASSIST HB GATE VALVES INSPECTION |  |  |  | 75%
A1820 | BWM HYDRAULIC SPRING ASSIST HB GATE VALVES INSPECTION |  |  |  | 75%
A1820 | BWM HYDRAULIC SPRING ASSIST HB GATE VALVES INSPECTION |  |  |  | 75%
A1820 | BWM HYDRAULIC SPRING ASSIST HB GATE VALVES INSPECTION |  |  |  | 75%
A1820 | BWM HYDRAULIC SPRING ASSIST HB GATE VALVES INSPECTION |  |  |  | 75%
A1820 | BWM HYDRAULIC SPRING ASSIST HB GATE VALVES INSPECTION |  |  |  | 75%
A1820 | BWM HYDRAULIC SPRING ASSIST HB GATE VALVES INSPECTION |  |  |  | 75%
A1820 | BWM HYDRAULIC SPRING ASSIST HB GATE VALVES INSPECTION |  |  |  | 75%
A1820 | BWM HYDRAULIC SPRING ASSIST HB GATE VALVES INSPECTION |  |  |  | 75%
A1820 | BWM HYDRAULIC SPRING ASSIST HB GATE VALVES INSPECTION |  |  |  | 75%
GENERAL COMMENTS
2026-Sep-30: Offline maintenance start