## Slide 1: SACRED
How it works today, what it needs, and how we move it off a laptop
Dan Plant · Well Control Equipment · for the transfer sit-down with Adam Snyder
Notes: Purpose of the meeting: agree the host (server or Microsoft web app), the identities, and the transfer day. Thirty minutes.

## Slide 2: SACRED in one slide
What it is
One set of web pages for Well Control Equipment: reports from every rig, planning, the Help Centre, the schedule builder and the certificate tracker. Opened in a browser, no install, no login on the rig.
Who uses it
16 rigs post reports. Office, superintendents, SMEs and the VP read the dashboards. Power Automate sends the emails and Teams posts.
What is live
Posting from the rigs since August. About 400 reports on the server. Nine automation loops. Database export for Fabric every run (36 tables).
Everything already runs on the Seadrill network. The only piece on a laptop is the script that turns posts into pages, the scanner. That is what we are moving.
Ask of this meeting: pick the host, confirm the identities Janzen has requested, book the transfer day.

## Slide 3: The loop, start to finish
1 Rig tool
A crew fills in a report in a browser tool (a single HTML file on the rig PC or tablet).
2 Post
The tool sends a JSON file over HTTPS to a Power Automate HTTP intake. No SharePoint rights on the rig.
3 SharePoint
The flow drops the file in WellControl / PostedReports. The posts are safe here whatever happens downstream.
4 Scanner
A PowerShell script, every 10 minutes, reads new posts, builds the data files and the database export.
5 Server
The scanner copies pages and data to the SACRED share on sdrlazneuiis01d. IIS serves them as plain web pages.
6 Notify
Flows read the scanner's output and send the emails and Teams posts (Help Centre, AABs, plans, precharge).
Where things are: rig tools and the intake flow are Seadrill Power Automate; the posts live in SharePoint (M365); the pages are served by IIS on the sandbox server. The orange step is the only one on a laptop.
Notes: Walk left to right. Stress step 3: SharePoint is the system of record, so nothing is lost if the scanner is off. Step 4 is the laptop.

## Slide 4: What the server serves today
1
Reports dashboard
Every post by rig and type, CBM, BWM, daily logs, pre-deployment checklists, errors list.
2
Status page
Nine automation loops with their health, per rig: checks, precharge, AAB acknowledgements, help, SSCE.
3
Help Centre
Assistance requests and the Plans tab where each committee position verifies a maintenance plan.
4
Argo Navis
Lee's schedule builder, served from the server with its data folder refreshed by the scanner.
5
CoC Tracker
Certificate status for the fleet, rebuilt from the Maximo extract every run (scanner v2.92).
6
Precharge inbox and AABs
Precharge requests issued from posts; advisory bulletins with rig acknowledgements.
7
Database export
36 tables, 22,600 rows every run, ready for Fabric.
8
Digests
One text digest per report for Copilot and Ask SACRED AI.

## Slide 5: Why the scanner must leave the laptop
10
minutes between runs, every day, as a scheduled task on Dan's PC
1
person. Laptop closed, on a plane, on leave: the dashboards stop refreshing and the notifications stop
0
data at risk. Every post is in SharePoint before the scanner ever sees it; the scanner can be re-run from scratch
What the scanner is
One PowerShell script (Windows PowerShell 5.1, no other software) and one config file. It reads a SharePoint library, reads two network shares for the Maximo extracts and Lee's inputs, writes pages and data to the web folder, and writes a database export. A full run takes 8 minutes on the laptop; most runs find nothing new and finish in seconds.

## Slide 6: What SACRED needs, whichever host
An identity that is not a person
Reads the SharePoint library and writes the web folder. Today it is Dan's login. Janzen Small (ISIT, Tech Services' app IT contact) requested two role accounts on 17 Oct: Well Control Group 1 and 2.
Somewhere to run on a schedule
Every 10 minutes, writing pages where the web server reads them.
HTTPS
Rig tablets can only install the pages for offline use over HTTPS. Also wanted for the schedule builder.
Role accounts and mailbox
The Well Control Group accounts with Exchange, Power Automate and Teams licences, so emails and Teams posts come from the department, not Dan, and access survives rotations and shared tablets.
The inputs reachable
Manpreet's Maximo extract and Lee's job plans: today on \\SEADRILL23339. Wherever the scanner runs, it must read them.
Dan deploys every update
Dan drops every update himself (scanner, Argo Navis, precharge, pages): Lee sends his Argo Navis builds to Dan. Dan's write access to the deploy folders means no ticket per update.

## Slide 7: Option A: the sandbox server, as planned
What it takes
Service account on sdrlazneuiis01d running the scheduled task
SharePoint read for that account: OneDrive sync does not run under a service account, so a UNC path to the library or a read through the SharePoint API
Write to the SACRED share on the same box
HTTPS binding on the IIS site with a corporate certificate
Read access to \\SEADRILL23339 from the server
Write access for Dan to the deploy folders
For
Smallest change: the pages are already served here. The scanner config changes one path. The rigs' bookmarks stay. Proven in two weeks of running against this server.
Against
A sandbox server, not production: ISIT still has to name the production home and plan a second cutover. HTTPS, certificate and service account are three separate tickets.

## Slide 8: Option B: a Microsoft web app, as Adam raised
What it would look like
Azure App Service hosts the pages as they are: they are static files
The scanner runs as a scheduled WebJob on the same app and writes into the app's own web root
SharePoint read through the Microsoft Graph API with an app registration (the change we need for a non-person identity anyway)
HTTPS is built in: the tablet request falls away
Azure cannot see \\SEADRILL23339, so the Maximo extract and Lee's inputs go into a SharePoint library and the scanner reads them there, the same way it reads the posts
For
Production from day one, ISIT's standard platform, HTTPS and identity handled the Microsoft way. Nothing changes for the rig tools: they post to the same flow.
To settle
Internet-facing with a Seadrill sign-in, or private network only? Rigs open SACRED today with no login. Where does the CoC Tracker file the rigs open go? Who creates the app registration and when?

## Slide 9: Side by side
 | A: sandbox server | B: Microsoft web app
Pages | Already there | Copied as they are
Scanner | Scheduled task, service account | Scheduled WebJob on the app
Reads SharePoint by | UNC path or SharePoint API | Graph API, app registration
HTTPS | New binding and certificate (ticket) | Built in
Maximo extract and Lee's inputs | Read from \\SEADRILL23339 | Moved into a SharePoint library
Rig tools and intake flow | Unchanged | Unchanged
Rig bookmarks | Unchanged | New address once
Sign-in for readers | None, as today | To be decided
Production status | Sandbox, second cutover later | Production from the start
Work on the scanner | One path in config | Config plus the Graph read

## Slide 10: What changes for a rig under either option
Nothing
for the posting tools. SSORT, WCGRRT and the checklist tools post to the same Power Automate address with the same key. No rebuild, no redeploy to 16 rigs.
Bookmarks
Server: unchanged. Web app: one new address, sent once with the class on 20 October.
Sign-in
Server: none, as today. Web app: depends on the decision above; a rig test is needed before cutover.
Offline tablets
Both give HTTPS in the end; the web app gives it on day one.

## Slide 11: Risk and fallback
The posts are never at risk
They land in SharePoint before the scanner runs. A scanner that is off for a day catches up on the next run; it has done so before.
The laptop stays on
Dan's scheduled task keeps running until the new host has produced one clean full run and the Status page agrees.
The scanner is one file
Same script on either host; the config names the paths. Rolling back is turning the laptop task back on.
Two things are secret
The intake key in the rig tools and the flow URL. Neither moves; neither is in the pages.

## Slide 12: Transfer day, in order
Before
Identity created and tested: can it read PostedReports and write the web folder? Well Control Group role accounts requested by Janzen (17 Oct).
Hour 1
Copy the scanner and config to the host. Point config at the host's paths. Run once by hand with the laptop task paused.
Hour 2
Compare the host's output with the laptop's: same report count, same Status page. Fix paths, run again.
Hour 3
Schedule the task or WebJob. Re-enable nothing on the laptop. Watch three runs.
Same day
Flows re-pointed if the address changed. Rigs told the address if it changed. Laptop task disabled, script kept.
Week after
Dan's deploy access confirmed, the extract library, HTTPS check from a rig tablet, the role accounts swapped into the flows.

## Slide 13: Decisions wanted today
1 Server or web app, and if web app: internet with sign-in, or private
2 The identity: Janzen's two role accounts (requested 17 Oct). Confirm one runs the scanner, or an app registration as well
3 The role accounts' Exchange, Power Automate and Teams licences, and who owns them
4 The transfer day and the one-hour window with Adam in the room
5 Later, not today: eDocs connector API key (asked of Digital Desk, 17 Oct; Dan's account until the role accounts land), Fabric capacity