## Proposed rows
Job Plan | Description | SFI | Proposed Branch | Proposed Parallel Group | Proposed Rank | Proposed Predecessors | Duration (h) - Durations workbook | Duration (h) - saved Maximo job plan | Open WOs | Rigs | Example Location | Confidence | Basis
0900-BT90022 | 60M AHC ACCUMULATOR INSPECTION | 302 | Offline Ancillary | 302 — Heave / motion compensation | 500 |  |  | 24 | 15 | Sevan Louisiana; Sonangol Quenguela; West Carina; West Saturn; West Tellus; West Vela | 302.AHC2 | Medium | SFI 302 is rig equipment off the BOP stack and control system, so it runs in parallel with BOP work (Offline Ancillary); one parallel group per SFI. No mapped plan at these locations to vote from - review the branch and rank.
0900-BT90023 | 120M AHC ACCUMULATOR OVERHAUL | 302 | Offline Ancillary | 302 — Heave / motion compensation | 500 |  |  | 48 | 15 | Sevan Louisiana; Sonangol Quenguela; West Carina; West Saturn; West Tellus; West Vela | 302.AHC1 | Medium | SFI 302 is rig equipment off the BOP stack and control system, so it runs in parallel with BOP work (Offline Ancillary); one parallel group per SFI. No mapped plan at these locations to vote from - review the branch and rank.
0900-BQ0912 | 12M ACTIVE HEAVE COMPENSATOR SERVICE | 302 | Offline Ancillary | 302 — Heave / motion compensation | 500 |  |  | 6 | 9 | West Auriga; West Carina; West Gemini; West Polaris; West Tellus | 302.AHC2 | Medium | SFI 302 is rig equipment off the BOP stack and control system, so it runs in parallel with BOP work (Offline Ancillary); one parallel group per SFI. No mapped plan at these locations to vote from - review the branch and rank.
0900-BQ0914 | 60M ACTIVE HEAVE COMPENSATOR INSPECTION | 302 | Offline Ancillary | 302 — Heave / motion compensation | 500 |  |  | 24 | 9 | Sonangol Quenguela; West Carina; West Saturn; West Tellus; West Vela | 302.AHC2 | Medium | SFI 302 is rig equipment off the BOP stack and control system, so it runs in parallel with BOP work (Offline Ancillary); one parallel group per SFI. No mapped plan at these locations to vote from - review the branch and rank.
0900-BQ0917 | 12M CROWN MOUNTED COMPENSATOR SERVICE | 302 | Offline Ancillary | 302 — Heave / motion compensation | 500 |  |  | 8 | 7 | West Carina; West Gemini; West Polaris; West Tellus; West Vela | 302.CMC1 | Medium | SFI 302 is rig equipment off the BOP stack and control system, so it runs in parallel with BOP work (Offline Ancillary); one parallel group per SFI. No mapped plan at these locations to vote from - review the branch and rank.
0900-BQ0911 | 3M ACTIVE HEAVE COMPENSATOR SERVICE | 302 | Offline Ancillary | 302 — Heave / motion compensation | 500 |  |  | 6 | 6 | Sonangol Libongos; West Gemini; West Neptune; West Tellus; West Vela | 302.AHC1 | Medium | SFI 302 is rig equipment off the BOP stack and control system, so it runs in parallel with BOP work (Offline Ancillary); one parallel group per SFI. No mapped plan at these locations to vote from - review the branch and rank.
0900-BQ0916 | 3M CROWN MOUNTED COMPENSATOR SERVICE | 302 | Offline Ancillary | 302 — Heave / motion compensation | 500 |  |  | 6 | 6 | Sonangol Libongos; West Gemini; West Neptune; West Tellus; West Vela | 302.CMC2 | Medium | SFI 302 is rig equipment off the BOP stack and control system, so it runs in parallel with BOP work (Offline Ancillary); one parallel group per SFI. No mapped plan at these locations to vote from - review the branch and rank.
0900-BQ0902 | 3M CROWN MOUNTED COMPENSATOR SERVICE | 302 | Offline Ancillary | 302 — Heave / motion compensation | 500 |  |  | 6 | 5 | Sonangol Libongos; West Jupiter; West Neptune; West Saturn; West Tellus | 302.CMC1 | Medium | SFI 302 is rig equipment off the BOP stack and control system, so it runs in parallel with BOP work (Offline Ancillary); one parallel group per SFI. No mapped plan at these locations to vote from - review the branch and rank.
0900-BQ0927 | 120M ACTIVE HEAVE COMPENSATOR SERVICE | 302 | Offline Ancillary | 302 — Heave / motion compensation | 500 |  |  | 48 | 5 | West Gemini; West Saturn; West Vela | 302.AHC1 | Medium | SFI 302 is rig equipment off the BOP stack and control system, so it runs in parallel with BOP work (Offline Ancillary); one parallel group per SFI. No mapped plan at these locations to vote from - review the branch and rank.
0900-BQ0908 | 12M CROWN MOUNTED COMPENSATOR HANDLING TOOL SERVICE | 302 | Offline Ancillary | 302 — Heave / motion compensation | 500 |  |  | 6 | 4 | Sonangol Libongos; West Carina; West Jupiter; West Tellus | 302.CMC1.400 | Medium | SFI 302 is rig equipment off the BOP stack and control system, so it runs in parallel with BOP work (Offline Ancillary); one parallel group per SFI. No mapped plan at these locations to vote from - review the branch and rank.
0900-BQ0913 | 36M ACTIVE HEAVE COMPENSATOR REPLACE | 302 | Offline Ancillary | 302 — Heave / motion compensation | 500 |  |  | 12 | 4 | West Carina; West Neptune | 302.AHC2 | Medium | SFI 302 is rig equipment off the BOP stack and control system, so it runs in parallel with BOP work (Offline Ancillary); one parallel group per SFI. No mapped plan at these locations to vote from - review the branch and rank.
0900-BQ90021 | 6M CROWN MOUNTED COMPENSATOR SERVICE | 302 | Offline Ancillary | 302 — Heave / motion compensation | 500 |  |  | 2 | 4 | Sonangol Libongos; West Vela | 302.CMC2 | Medium | SFI 302 is rig equipment off the BOP stack and control system, so it runs in parallel with BOP work (Offline Ancillary); one parallel group per SFI. No mapped plan at these locations to vote from - review the branch and rank.
0900-IF0802 | 3M CMC INCREASE / DECREASE CABINET INSPECTION | 302 | Offline Ancillary | 302 — Heave / motion compensation | 500 |  |  | 3 | 4 | West Jupiter; West Neptune; West Saturn; West Vela | 302.CMC2 | Medium | SFI 302 is rig equipment off the BOP stack and control system, so it runs in parallel with BOP work (Offline Ancillary); one parallel group per SFI. No mapped plan at these locations to vote from - review the branch and rank.
0900-IF0803 | 3M CMC MAIN AIR VALVE CABINET INSPECTION | 302 | Offline Ancillary | 302 — Heave / motion compensation | 500 |  |  | 3 | 4 | West Jupiter; West Neptune; West Saturn; West Vela | 302.CMC2 | Medium | SFI 302 is rig equipment off the BOP stack and control system, so it runs in parallel with BOP work (Offline Ancillary); one parallel group per SFI. No mapped plan at these locations to vote from - review the branch and rank.
0900-IF0804 | 3M CMC MAIN AIR VALVE CABINET SERVICE | 302 | Offline Ancillary | 302 — Heave / motion compensation | 500 |  |  | 3 | 4 | West Jupiter; West Neptune; West Saturn; West Vela | 302.CMC1 | Medium | SFI 302 is rig equipment off the BOP stack and control system, so it runs in parallel with BOP work (Offline Ancillary); one parallel group per SFI. No mapped plan at these locations to vote from - review the branch and rank.
0900-BA80078 | 12M CROWN BLOCK MECHANICAL CONDITION ASSESSMENT | 302 | Offline Ancillary | 302 — Heave / motion compensation | 500 |  |  |  | 3 | Sonangol Libongos; West Carina | 302.CRB2 | Medium | SFI 302 is rig equipment off the BOP stack and control system, so it runs in parallel with BOP work (Offline Ancillary); one parallel group per SFI. No mapped plan at these locations to vote from - review the branch and rank.
0900-KB85101 | 12M COMPRESSOR ELECTRICAL INSPECTION | 315 | Offline Ancillary | 315 — Subsea support utilities | 500 |  |  |  | 3 | West Capella | 315.HPC1.120 | Medium | SFI 315 is rig equipment off the BOP stack and control system, so it runs in parallel with BOP work (Offline Ancillary); one parallel group per SFI. No mapped plan at these locations to vote from - review the branch and rank.
0900-KD91961 | 12M RIG AIR DRYER/COMPRESSOR TEST | 315 | Offline Ancillary | 315 — Subsea support utilities | 500 |  |  |  | 3 | West Capella | 315.HPC1.130 | Medium | SFI 315 is rig equipment off the BOP stack and control system, so it runs in parallel with BOP work (Offline Ancillary); one parallel group per SFI. No mapped plan at these locations to vote from - review the branch and rank.
0900-BQ0918 | 60M CROWN MOUNTED COMPENSATOR INSPECTION | 302 | Offline Ancillary | 302 — Heave / motion compensation | 500 |  |  | 24 | 3 | Sonangol Quenguela; West Saturn; West Vela | 302.CMC2 | Medium | SFI 302 is rig equipment off the BOP stack and control system, so it runs in parallel with BOP work (Offline Ancillary); one parallel group per SFI. No mapped plan at these locations to vote from - review the branch and rank.
0900-CV80023 | 12M MAIN RINGLINE HPU SERVICE | 302 | Offline Ancillary | 302 — Heave / motion compensation | 500 |  |  |  | 2 | Sevan Louisiana; West Gemini | 302.AHC2.200 | Medium | SFI 302 is rig equipment off the BOP stack and control system, so it runs in parallel with BOP work (Offline Ancillary); one parallel group per SFI. No mapped plan at these locations to vote from - review the branch and rank.
0900-EE90051 | 12M EMERGENCY STOP ELECTRICAL TEST | 315 | Offline Ancillary | 315 — Subsea support utilities | 500 |  |  |  | 2 | West Carina | 315.HPC1.120 | Medium | SFI 315 is rig equipment off the BOP stack and control system, so it runs in parallel with BOP work (Offline Ancillary); one parallel group per SFI. No mapped plan at these locations to vote from - review the branch and rank.
0900-BQ0904 | 12M CROWN MOUNTED COMPENSATOR SERVICE | 302 | Offline Ancillary | 302 — Heave / motion compensation | 500 |  |  | 5 | 2 | West Carina; West Vela | 302.CMC1 | Medium | SFI 302 is rig equipment off the BOP stack and control system, so it runs in parallel with BOP work (Offline Ancillary); one parallel group per SFI. No mapped plan at these locations to vote from - review the branch and rank.
0900-BQ0905 | 60M CROWN MOUNTED COMPENSATOR INSPECTION | 302 | Offline Ancillary | 302 — Heave / motion compensation | 500 |  |  | 24 | 2 | Sonangol Quenguela; West Vela | 302.CMC1 | Medium | SFI 302 is rig equipment off the BOP stack and control system, so it runs in parallel with BOP work (Offline Ancillary); one parallel group per SFI. No mapped plan at these locations to vote from - review the branch and rank.
0900-CV80021 | 1M RINGLINE HPU INSPECTION | 302 | Offline Ancillary | 302 — Heave / motion compensation | 500 |  |  |  | 1 | Sevan Louisiana | 302.AHC1.200 | Medium | SFI 302 is rig equipment off the BOP stack and control system, so it runs in parallel with BOP work (Offline Ancillary); one parallel group per SFI. No mapped plan at these locations to vote from - review the branch and rank.
0900-EJ90051 | 12M JUNCTION BOX ELECTRICAL INSPECTION | 302 | Offline Ancillary | 302 — Heave / motion compensation | 500 |  |  |  | 1 | Sevan Louisiana | 302.CMC1 | Medium | SFI 302 is rig equipment off the BOP stack and control system, so it runs in parallel with BOP work (Offline Ancillary); one parallel group per SFI. No mapped plan at these locations to vote from - review the branch and rank.
0900-QZ90261 | 48M MRU ELECTRICAL SERVICE | 302 | Offline Ancillary | 302 — Heave / motion compensation | 500 |  |  |  | 1 | West Vela | 302.AHC1 | Medium | SFI 302 is rig equipment off the BOP stack and control system, so it runs in parallel with BOP work (Offline Ancillary); one parallel group per SFI. No mapped plan at these locations to vote from - review the branch and rank.
0900-BQ0909 | 60M CROWN MOUNTED COMPENSATOR HANDLING TOOL OVERHAUL | 302 | Offline Ancillary | 302 — Heave / motion compensation | 500 |  |  | 24 | 1 | West Vela | 302.CMC1.400 | Medium | SFI 302 is rig equipment off the BOP stack and control system, so it runs in parallel with BOP work (Offline Ancillary); one parallel group per SFI. No mapped plan at these locations to vote from - review the branch and rank.
0900-BQ0910 | 1M ACTIVE HEAVE COMPENSATOR SERVICE | 302 | Offline Ancillary | 302 — Heave / motion compensation | 500 |  |  | 4 | 1 | West Gemini | 302.AHC1 | Medium | SFI 302 is rig equipment off the BOP stack and control system, so it runs in parallel with BOP work (Offline Ancillary); one parallel group per SFI. No mapped plan at these locations to vote from - review the branch and rank.
0900-BQ0915 | 1M CROWN MOUNTED COMPENSATOR | 302 | Offline Ancillary | 302 — Heave / motion compensation | 500 |  |  | 4 | 1 | West Gemini | 302.CMC1 | Medium | SFI 302 is rig equipment off the BOP stack and control system, so it runs in parallel with BOP work (Offline Ancillary); one parallel group per SFI. No mapped plan at these locations to vote from - review the branch and rank.
0900-BQ0926 | 120M CROWN MOUNTED COMPENSATOR OVERHAUL | 302 | Offline Ancillary | 302 — Heave / motion compensation | 500 |  |  | 48 | 1 | West Saturn | 302.CMC1 | Medium | SFI 302 is rig equipment off the BOP stack and control system, so it runs in parallel with BOP work (Offline Ancillary); one parallel group per SFI. No mapped plan at these locations to vote from - review the branch and rank.
0900-BQ0929 | 120M CROWN MOUNTED COMPENSATOR OVERHAUL | 302 | Offline Ancillary | 302 — Heave / motion compensation | 500 |  |  | 48 | 1 | West Saturn | 302.CMC2 | Medium | SFI 302 is rig equipment off the BOP stack and control system, so it runs in parallel with BOP work (Offline Ancillary); one parallel group per SFI. No mapped plan at these locations to vote from - review the branch and rank.

## Read me
DRAFT for Dan: proposed Branch & Sequence Map rows for the SFI 302 (heave / motion compensation) and 315 (subsea support utilities) job plans that arrived in Manpreet's extract of 15 Oct.
31 job plans, 129 open WOs fleet-wide. Not on either sheet of the map today, so their WOs read Unassigned in Argo Navis.
Proposed: Branch = Offline Ancillary (rig equipment, in parallel with BOP work); Parallel Group = the SFI group; Rank 500; no predecessors. No mapped plan exists at these locations to vote from, so every row is Medium confidence: please review.
Durations: where Job Plans and Durations has none, the saved Maximo job plan's duration is shown for reference.
Dan's map is not edited. Argo Navis reads the map from the share.