## Read me
Branch & Sequence Map additions - DRAFT for Dan Plant
- Prepared 13 Oct 2026 by Argo Navis for Lee Arnold, for Dan to review. Nothing has been changed in Job Plan Branch Sequence Map.xlsx.
- Why: 36 job plans used by open in-scope work orders are on neither sheet of the Branch Map, so Argo Navis shows them as "Unassigned" (not sequenced). Lee has now exported all of them from Maximo (Job plan detailed - missing plans 2026-10-13.xlsx).
- Proposed rows (sheet 2) are in the Branch Map's own column order (A-L), so a reviewed row can be copied straight across. Columns M onwards (REVIEW, yellow) are for the review only.
- Method: each plan takes the Branch / Parallel Group used by the existing mapped plans whose work orders sit at the same Maximo locations (weighted by work orders); if none share a location, the same equipment group (e.g. 331.BOP). Sequence Rank and Predecessors are copied from the closest-described plan in that group ("Modelled on") - many of these are site variants (e.g. 0900-UB90122 vs 0900-UB90021).
- Confidence: High = same location and at least 70% of the mapped work there agrees; Medium = a majority agrees; Low = weak evidence (0900-EE90061, 0900-XX90021) - place by judgement.
- Durations: Argo Navis now uses each plan's Maximo job plan duration where Job Plans and Durations.xlsm has none, flagged "Maximo" in the tool.
- Sheet 3 lists the 12 in-scope plans already on your Excluded sheet. They are not proposed; Argo Navis now reads that sheet and defers their work orders by default with a red badge.
- Still missing from Lee's export: 0900-UR0007 and 0900-UR90021 (no saved job plan).

## Proposed rows
Job Plan | Description | Event | Rigs In Use (Known) | Build Priority Block | Branch | Parallel Group | Sequence Rank | Predecessor Job Plan(s) | Notes | SFI Group ID (ref) | Object Type (ref) | REVIEW: Confidence | REVIEW: Basis | REVIEW: Modelled on | REVIEW: Model description | REVIEW: Open WOs | REVIEW: Rigs | REVIEW: Locations | REVIEW: Maximo duration (h) | REVIEW: In Durations workbook
0900-UB90122 | 12M NXT BOP BODY INSPECTION |  |  |  | Lower BOP | Lower BOP General | 79 |  | DRAFT 13 Oct 2026 - proposed by Argo Navis from the existing map; review before adding | 331 | UB | High | same location: 73% of mapped work there is Lower BOP / Lower BOP General; nearest plan by description 0900-UB90021 (33% match) | 0900-UB90021 | 60M RAM BODY INSPECTION | 14 | West Tellus; West Jupiter | 331.BOP.360, 331.BOP.370, 331.BOP.340, 331.BOP.350, 331.BOP.310, 331.BOP.330, 331.BOP.320 | 2 | no - Argo Navis uses the Maximo duration (flagged)
0900-UB90129 | BWM RAM BLOCKS INSPECTION | BWM |  |  | Lower BOP | Lower BOP General | 33 |  | DRAFT 13 Oct 2026 - proposed by Argo Navis from the existing map; review before adding | 331 | UB | High | same location: 91% of mapped work there is Lower BOP / Lower BOP General; nearest plan by description 0900-UB0214 (67% match) | 0900-UB0214 | 12M PIPE RAM BLOCK INSPECTION | 14 | West Jupiter | 331.BOP.314, 331.BOP.324, 331.BOP.334, 331.BOP.344, 331.BOP.354, 331.BOP.364, 331.BOP.375, 331.BOP.315, 331.BOP.335, 331.BOP.325, 331.BOP.345, 331.BOP.355, 331.BOP.365, 331.BOP.374 | 3 | no - Argo Navis uses the Maximo duration (flagged)
0900-IF0003 | 12M LOCAL CONTROL PANEL INSPECTION |  |  |  | Offline Ancillary | Utility Systems | 1 |  | DRAFT 13 Oct 2026 - proposed by Argo Navis from the existing map; review before adding | 339/337 | IF | High | same location: 89% of mapped work there is Offline Ancillary / Utility Systems; nearest plan by description 0900-IU0001 (0% match) | 0900-IU0001 | 12M TEST MANDREL FOR BOP - NDE INSPECTION | 13 | West Polaris; West Vela; West Neptune; West Jupiter; West Carina; Sevan Louisiana | 339.MPD.500, 339.MPD.1250, 339.MPD.1210, 339.MPD.1240, 337.MWC | 1.5 | no - Argo Navis uses the Maximo duration (flagged)
0900-EE90061 | 12M GENERAL INSTRUMENTATION ELECTRICAL INSPECTION |  |  |  | Offline Ancillary | Utility Systems | 1 |  | DRAFT 13 Oct 2026 - proposed by Argo Navis from the existing map; review before adding | 339/336/337 | EE | Low | same location: 40% of mapped work there is Offline Ancillary / Utility Systems; nearest plan by description 0900-IU0001 (0% match) | 0900-IU0001 | 12M TEST MANDREL FOR BOP - NDE INSPECTION | 13 | West Polaris; West Capella; West Gemini; West Neptune; West Jupiter; West Carina | 339.MPD.500, 339.MPD.1100, 336.MGS, 337.MWC | 1 | no - Argo Navis uses the Maximo duration (flagged)
0900-EF90051 | 12M MOTOR AND STARTER ELECTRICAL INSPECTION |  |  |  | Offline Ancillary | Utility Systems | 1 |  | DRAFT 13 Oct 2026 - proposed by Argo Navis from the existing map; review before adding | 337/339/332 | EF | High | same location: 73% of mapped work there is Offline Ancillary / Utility Systems; nearest plan by description 0900-IU0001 (0% match) | 0900-IU0001 | 12M TEST MANDREL FOR BOP - NDE INSPECTION | 13 | West Gemini; West Vela; West Neptune; West Jupiter; West Carina | 337.MWC, 339.MPD.1100, 332.BCSS.210, 332.BCSS.220, 332.BCSS.340, 332.BCSS.350, 332.BCSS.360 | 2 | no - Argo Navis uses the Maximo duration (flagged)
0900-EE5006 | 12M INSTRUMENTATION ELECTRICAL INSPECTION |  |  |  | Offline Ancillary | Riser System | 3 |  | DRAFT 13 Oct 2026 - proposed by Argo Navis from the existing map; review before adding | 335 | EE | High | same location: 100% of mapped work there is Offline Ancillary / Riser System; nearest plan by description 0900-BR0201 (0% match) | 0900-BR0201 | BWM NOV TENSION RING ASSEMBLY INSPECTION | 12 | Sonangol Quenguela; West Auriga; West Vela; West Tellus; West Jupiter; West Saturn | 335.RIS.650, 335.RIS.660 | 2 | no - Argo Navis uses the Maximo duration (flagged)
0900-UB90125 | 12M POSLOCK DOOR INSPECTION |  |  |  | Lower BOP | Lower BOP General | 28 |  | DRAFT 13 Oct 2026 - proposed by Argo Navis from the existing map; review before adding | 331 | UB | High | same location: 91% of mapped work there is Lower BOP / Lower BOP General; nearest plan by description 0900-UB0209 (25% match) | 0900-UB0209 | 24M SHEAR RAM POSLOCK SERVICE | 12 | West Tellus; West Jupiter | 331.BOP.333, 331.BOP.313, 331.BOP.332, 331.BOP.312, 331.BOP.323, 331.BOP.322 | 6 | no - Argo Navis uses the Maximo duration (flagged)
0900-RG90021 | BWM FAILSAFE VALVES INSPECTION | BWM |  |  | Lower BOP | Lower BOP General | 2 |  | DRAFT 13 Oct 2026 - proposed by Argo Navis from the existing map; review before adding | 331/335 | RG | High | same location: 100% of mapped work there is Lower BOP / Lower BOP General; nearest plan by description 0900-RG0201 (14% match) | 0900-RG0201 | BWM HYDRAULIC SPRING ASSIST HB GATE VALVE INSPECTION | 9 | West Jupiter | 331.BOP.510, 331.LMRP.320, 331.LMRP.330, 335.RIS.510, 331.BOP.560, 331.BOP.550, 331.BOP.530, 331.LMRP.310, 331.BOP.540 | 2 | no - Argo Navis uses the Maximo duration (flagged)
0900-UC90022 | 12M C&K MINI CONNECTORS INSPECTION |  |  |  | Lower BOP | Lower BOP General | 90 |  | DRAFT 13 Oct 2026 - proposed by Argo Navis from the existing map; review before adding | 331 | UC | High | same location: 100% of mapped work there is Lower BOP / Lower BOP General; nearest plan by description 0900-UC0117 (40% match) | 0900-UC0117 | 30M MINI COLLET CONNECTOR OVERHAUL | 8 | West Tellus; West Jupiter | 331.BOP.120, 331.LMRP.420, 331.LMRP.410, 331.BOP.130 | 4 | no - Argo Navis uses the Maximo duration (flagged)
0900-UB90126 | BWM ULTRALOCK DOOR INSPECTION | BWM |  |  | Lower BOP | Lower BOP General | 80 |  | DRAFT 13 Oct 2026 - proposed by Argo Navis from the existing map; review before adding | 331 | UB | Medium | same location: 57% of mapped work there is Lower BOP / Lower BOP General; nearest plan by description 0900-UB90128 (67% match) | 0900-UB90128 | 12M ULTRALOCK DOOR FUNCTION & CHAMBER TEST | 8 | West Jupiter | 331.BOP.363, 331.BOP.352, 331.BOP.373, 331.BOP.362, 331.BOP.342, 331.BOP.353, 331.BOP.372, 331.BOP.343 | 2 | no - Argo Navis uses the Maximo duration (flagged)
0900-UB90121 | BWM NXT BOP BODY INSPECTION | BWM |  |  | Lower BOP | Lower BOP General | 79 |  | DRAFT 13 Oct 2026 - proposed by Argo Navis from the existing map; review before adding | 331 | UB | High | same location: 73% of mapped work there is Lower BOP / Lower BOP General; nearest plan by description 0900-UB90021 (33% match) | 0900-UB90021 | 60M RAM BODY INSPECTION | 7 | West Jupiter | 331.BOP.310, 331.BOP.320, 331.BOP.330, 331.BOP.340, 331.BOP.350, 331.BOP.360, 331.BOP.370 | 2 | no - Argo Navis uses the Maximo duration (flagged)
0900-UB90022 | 12M RAM BLOCKS NDE INSPECTION |  |  |  | Lower BOP | Lower BOP General | 81 |  | DRAFT 13 Oct 2026 - proposed by Argo Navis from the existing map; review before adding | 331 | UB | High | same location: 79% of mapped work there is Lower BOP / Lower BOP General; nearest plan by description 0900-UB90220 (60% match) | 0900-UB90220 | 12M LFS-5 SHEAR RAM BLOCKS NDE INSPECTION | 6 | West Tellus | 331.BOP.335, 331.BOP.314, 331.BOP.334, 331.BOP.315, 331.BOP.324, 331.BOP.325 | 2 | no - Argo Navis uses the Maximo duration (flagged)
0900-UB90124 | BWM POSLOCK DOOR INSPECTION | BWM |  |  | Lower BOP | Lower BOP General | 28 |  | DRAFT 13 Oct 2026 - proposed by Argo Navis from the existing map; review before adding | 331 | UB | High | same location: 91% of mapped work there is Lower BOP / Lower BOP General; nearest plan by description 0900-UB0209 (25% match) | 0900-UB0209 | 24M SHEAR RAM POSLOCK SERVICE | 6 | West Jupiter | 331.BOP.312, 331.BOP.313, 331.BOP.322, 331.BOP.332, 331.BOP.333, 331.BOP.323 | 1 | no - Argo Navis uses the Maximo duration (flagged)
0900-IA5000 | 12M PLC ELECTRICAL INSPECTION |  |  |  | Offline Ancillary | MPD | 21 |  | DRAFT 13 Oct 2026 - proposed by Argo Navis from the existing map; review before adding | 339/314 | IA | Medium | same location: 55% of mapped work there is Offline Ancillary / MPD; nearest plan by description 0900-CV85001 (0% match) | 0900-CV85001 | 12M GLYCOL INJECTION UNIT ELECTRICAL INSPECTION | 5 | West Capella; West Neptune; West Saturn; West Carina | 339.MPD.1100, 314.WLT | 1 | no - Argo Navis uses the Maximo duration (flagged)
0900-UA90022 | 12M SBOP INSPECTION |  |  |  | LMRP | Annulars | 6 |  | DRAFT 13 Oct 2026 - proposed by Argo Navis from the existing map; review before adding | 331 | UA | High | same location: 100% of mapped work there is LMRP / Annulars; nearest plan by description 0900-UA0201 (0% match) | 0900-UA0201 | BWM ANNULAR BOP INSPECTION | 4 | West Tellus; West Jupiter | 331.LMRP.600, 331.LMRP.700 | 4 | no - Argo Navis uses the Maximo duration (flagged)
0900-UC90021 | BWM C&K MINI CONNECTORS INSPECTION | BWM |  |  | Lower BOP | Lower BOP General | 90 |  | DRAFT 13 Oct 2026 - proposed by Argo Navis from the existing map; review before adding | 331 | UC | High | same location: 100% of mapped work there is Lower BOP / Lower BOP General; nearest plan by description 0900-UC0117 (40% match) | 0900-UC0117 | 30M MINI COLLET CONNECTOR OVERHAUL | 4 | West Jupiter | 331.BOP.120, 331.BOP.130, 331.LMRP.410, 331.LMRP.420 | 2 | no - Argo Navis uses the Maximo duration (flagged)
0900-EB5000 | 12M BATTERY CHARGER / UPS ELECTRICAL INSPECTION |  |  |  | Controls | Control System | 92 |  | DRAFT 13 Oct 2026 - proposed by Argo Navis from the existing map; review before adding | 332 | EB | High | same location: 100% of mapped work there is Controls / Control System; nearest plan by description 0900-EB0101 (33% match) | 0900-EB0101 | BWM BOP UPS ELECTRICAL INSPECTION | 4 | West Jupiter; West Carina | 332.BCSS.811, 332.BCSS.812 | 1.5 | no - Argo Navis uses the Maximo duration (flagged)
0900-RH90121 | BWM SPOOLS & BLOCKS INSPECTION | BWM |  |  | Lower BOP | Lower BOP General | 6 |  | DRAFT 13 Oct 2026 - proposed by Argo Navis from the existing map; review before adding | 331 | RH | High | same location: 84% of mapped work there is Lower BOP / Lower BOP General; nearest plan by description 0900-RH0202 (25% match) | 0900-RH0202 | BWM BOP SUBSEA CHOKE AND KILL SPOOL INSPECTION | 3 | West Jupiter | 331.BOP.610, 331.BOP.620, 331.LMRP.500 | 1 | no - Argo Navis uses the Maximo duration (flagged)
0900-EB90055 | 60M UPS ELECTRICAL INSPECTION |  |  |  | Offline Ancillary | MPD | 21 |  | DRAFT 13 Oct 2026 - proposed by Argo Navis from the existing map; review before adding | 332/339 | EB | High | same location: 100% of mapped work there is Offline Ancillary / MPD; nearest plan by description 0900-CV85001 (0% match) | 0900-CV85001 | 12M GLYCOL INJECTION UNIT ELECTRICAL INSPECTION | 2 | Sonangol Quenguela; West Carina | 332.BCSS.810, 339.MPD.1220 | 2.5 | no - Argo Navis uses the Maximo duration (flagged)
0900-IA90061 | 6M INSTRUMENT (PLC / PC) CABINET INSPECTION |  |  |  | Offline Ancillary | MPD | 21 |  | DRAFT 13 Oct 2026 - proposed by Argo Navis from the existing map; review before adding | 339 | IA | Medium | same equipment group: 87% of mapped work there is Offline Ancillary / MPD; nearest plan by description 0900-CV85001 (0% match) | 0900-CV85001 | 12M GLYCOL INJECTION UNIT ELECTRICAL INSPECTION | 2 | West Polaris; West Vela | 339.MPD.1230 | 1 | no - Argo Navis uses the Maximo duration (flagged)
0900-CV90121 | BWM MPD UMBILICAL INSPECTION | BWM |  |  | Offline Ancillary | MPD | 14 |  | DRAFT 13 Oct 2026 - proposed by Argo Navis from the existing map; review before adding | 339 | CV | High | same location: 100% of mapped work there is Offline Ancillary / MPD; nearest plan by description 0900-CV0032 (67% match) | 0900-CV0032 | BWM MPD UMBILICAL REEL INSPECTION | 2 | West Polaris; West Neptune | 339.MPD.410 | 2 | no - Argo Navis uses the Maximo duration (flagged)
0900-BE90024 | BWM DIVERTER ASSEMBLY INSPECTION | BWM |  |  | Offline Ancillary | Diverter | 3 |  | DRAFT 13 Oct 2026 - proposed by Argo Navis from the existing map; review before adding | 334 | BE | High | same location: 71% of mapped work there is Offline Ancillary / Diverter; nearest plan by description 0900-BE0206 (100% match) | 0900-BE0206 | 12M DIVERTER ASSEMBLY (21 1/4" Shaffer) SERVICE | 2 | West Capella; West Tellus | 334.DIV.300 | 4 | no - Argo Navis uses the Maximo duration (flagged)
0900-EB5002 | 12M BATTERY CAPACITY/DRAW DOWN ELECTRICAL TEST |  |  |  | Offline Ancillary | MPD | 21 |  | DRAFT 13 Oct 2026 - proposed by Argo Navis from the existing map; review before adding | 339 | EB | High | same location: 100% of mapped work there is Offline Ancillary / MPD; nearest plan by description 0900-CV85001 (0% match) | 0900-CV85001 | 12M GLYCOL INJECTION UNIT ELECTRICAL INSPECTION | 2 | West Auriga; West Vela | 339.MPD.1220 | 3 | no - Argo Navis uses the Maximo duration (flagged)
0900-UR90122 | 12M RISER ADAPTER INSPECTION |  |  |  | Offline Ancillary | Riser System | 37 |  | DRAFT 13 Oct 2026 - proposed by Argo Navis from the existing map; review before adding | 335 | UR | High | same location: 100% of mapped work there is Offline Ancillary / Riser System; nearest plan by description 0900-UR0202 (100% match) | 0900-UR0202 | BWM RISER ADAPTER INSPECTION | 2 | West Tellus; West Jupiter | 335.RIS.410 | 4 | no - Argo Navis uses the Maximo duration (flagged)
0900-DP90021 | BWM NOV SHAFFER HYDRAULIC RISER RUNNING TOOL INSPECTION | BWM |  |  | Offline Ancillary | Riser System | 74 |  | DRAFT 13 Oct 2026 - proposed by Argo Navis from the existing map; review before adding | 335 | DP | High | same location: 100% of mapped work there is Offline Ancillary / Riser System; nearest plan by description 0900-DP0205 (100% match) | 0900-DP0205 | 12M NOV SHAFFER HYDRAULIC RISER RUNNING TOOL INSPECTION | 2 | West Tellus | 335.RIS.650, 335.RIS.660 | 3 | no - Argo Navis uses the Maximo duration (flagged)
0900-DP90022 | 12M NOV SHAFFER HYDRAULIC RISER RUNNING TOOL NDT |  |  |  | Offline Ancillary | Riser System | 74 |  | DRAFT 13 Oct 2026 - proposed by Argo Navis from the existing map; review before adding | 335 | DP | High | same location: 100% of mapped work there is Offline Ancillary / Riser System; nearest plan by description 0900-DP0205 (80% match) | 0900-DP0205 | 12M NOV SHAFFER HYDRAULIC RISER RUNNING TOOL INSPECTION | 2 | West Tellus | 335.RIS.650, 335.RIS.660 | 2 | no - Argo Navis uses the Maximo duration (flagged)
0900-UA90021 | BWM SBOP INSPECTION | BWM |  |  | LMRP | Annulars | 6 |  | DRAFT 13 Oct 2026 - proposed by Argo Navis from the existing map; review before adding | 331 | UA | High | same location: 100% of mapped work there is LMRP / Annulars; nearest plan by description 0900-UA0201 (0% match) | 0900-UA0201 | BWM ANNULAR BOP INSPECTION | 2 | West Jupiter | 331.LMRP.600, 331.LMRP.700 | 2 | no - Argo Navis uses the Maximo duration (flagged)
0900-RR90171 | 12M BX TITAN VALVE MECHANICAL SERVICE |  |  |  | Offline Ancillary | Choke and Kill | 25 |  | DRAFT 13 Oct 2026 - proposed by Argo Navis from the existing map; review before adding | 336 | RR | Medium | same location: 53% of mapped work there is Offline Ancillary / Choke and Kill; nearest plan by description 0900-RG0802 (20% match) | 0900-RG0802 | 60M CHOKE VALVES OVERHAUL | 1 | Sonangol Quenguela | 336.CK | 12 | no - Argo Navis uses the Maximo duration (flagged)
0900-XX90021 | OIL SAMPLING - 3.PARTY ANALYSIS ONSHORE |  |  |  | Controls | Control System | 135 |  | DRAFT 13 Oct 2026 - proposed by Argo Navis from the existing map; review before adding | 314 | XX | Low | no mapped plan shares its locations - placed by description only; review | 0900-XX0101 | 1M BOP FLUID SAMPLING INSPECTION | 1 | West Elara | 314.TEN | 1 | no - Argo Navis uses the Maximo duration (flagged)
0900-WW90022 | 12M NOV SHAFFER HYD. SPIDER GIMBAL AND CONTROL PANEL INSPECTION |  |  |  | Controls | Control System | 133 |  | DRAFT 13 Oct 2026 - proposed by Argo Navis from the existing map; review before adding | 335 | WW | High | same location: 100% of mapped work there is Controls / Control System; nearest plan by description 0900-WW0202 (100% match) | 0900-WW0202 | 12M NOV SHAFFER HYD. SPIDER GIMBAL AND CONTROL PANEL SERVICE | 1 | West Tellus | 335.RIS.600 | 6 | no - Argo Navis uses the Maximo duration (flagged)
0900-BE90022 | 12M DIVERTER HOUSING INSPECTION |  |  |  | Offline Ancillary | Diverter | 23 |  | DRAFT 13 Oct 2026 - proposed by Argo Navis from the existing map; review before adding | 334 | BE | High | same location: 100% of mapped work there is Offline Ancillary / Diverter; nearest plan by description 0900-BE0203 (100% match) | 0900-BE0203 | BWM DIVERTER HOUSING INSPECTION | 1 | West Tellus | 334.DIV.200 | 4 | no - Argo Navis uses the Maximo duration (flagged)
0900-BE90021 | BWM DIVERTER HOUSING INSPECTION | BWM |  |  | Offline Ancillary | Diverter | 23 |  | DRAFT 13 Oct 2026 - proposed by Argo Navis from the existing map; review before adding | 334 | BE | High | same location: 100% of mapped work there is Offline Ancillary / Diverter; nearest plan by description 0900-BE0203 (100% match) | 0900-BE0203 | BWM DIVERTER HOUSING INSPECTION | 1 | West Tellus | 334.DIV.200 | 4 | no - Argo Navis uses the Maximo duration (flagged)
0900-WW90021 | BWM NOV SHAFFER HYD. SPIDER GIMBAL AND CONTROL PANEL INSPECTION | BWM |  |  | Controls | Control System | 133 |  | DRAFT 13 Oct 2026 - proposed by Argo Navis from the existing map; review before adding | 335 | WW | High | same location: 100% of mapped work there is Controls / Control System; nearest plan by description 0900-WW0202 (100% match) | 0900-WW0202 | 12M NOV SHAFFER HYD. SPIDER GIMBAL AND CONTROL PANEL SERVICE | 1 | West Tellus | 335.RIS.600 | 3 | no - Argo Navis uses the Maximo duration (flagged)
0900-UE90021 | BWM BOP MANDREL INSPECTION | BWM |  |  | Lower BOP | Lower BOP General | 2 |  | DRAFT 13 Oct 2026 - proposed by Argo Navis from the existing map; review before adding | 331 | UE | High | same location: 100% of mapped work there is Lower BOP / Lower BOP General; nearest plan by description 0900-RG0201 (0% match) | 0900-RG0201 | BWM HYDRAULIC SPRING ASSIST HB GATE VALVE INSPECTION | 1 | West Jupiter | 331.BOP.110 | 2 | no - Argo Navis uses the Maximo duration (flagged)
0900-UR90121 | BWM RISER ADAPTER INSPECTION | BWM |  |  | Offline Ancillary | Riser System | 37 |  | DRAFT 13 Oct 2026 - proposed by Argo Navis from the existing map; review before adding | 335 | UR | High | same location: 100% of mapped work there is Offline Ancillary / Riser System; nearest plan by description 0900-UR0202 (100% match) | 0900-UR0202 | BWM RISER ADAPTER INSPECTION | 1 | West Jupiter | 335.RIS.410 | 1 | no - Argo Navis uses the Maximo duration (flagged)
0900-CU0004 | 1M OXYGEN MONITOR INSPECTION |  |  |  | Offline Ancillary | Utility Systems | 1 |  | DRAFT 13 Oct 2026 - proposed by Argo Navis from the existing map; review before adding | 337 | CU | High | same location: 92% of mapped work there is Offline Ancillary / Utility Systems; nearest plan by description 0900-IU0001 (0% match) | 0900-IU0001 | 12M TEST MANDREL FOR BOP - NDE INSPECTION | 1 | West Saturn | 337.MWC | 2 | no - Argo Navis uses the Maximo duration (flagged)

## Excluded (not proposed)
Job Plan | Description | Open WOs (in scope) | Rigs | Reason on the Excluded sheet | Branch (before exclusion) | Parallel Group (before exclusion)
0900-UB0101 | 7D BOP SUBSEA FUNCTION TEST | 20 | Sonangol Libongos; Sonangol Quenguela; West Capella; West Gemini; West Jupiter; West Neptune; West Polaris; West Saturn; West Vela | Flagged red - not done by subsea or electrical department | Testing | BOP
0900-UB0102 | 21D BOP SUBSEA PRESSURE TEST | 12 | Sonangol Libongos; Sonangol Quenguela; West Capella; West Gemini; West Jupiter; West Polaris; West Saturn; West Tellus; West Vela | Flagged red - not done by subsea or electrical department | Testing | BOP
0900-UB0224 | 21 DAYS ACOUSTIC CONTROL COMMUNICATION SUBSEA TEST | 8 | Sonangol Libongos; Sonangol Quenguela; West Auriga; West Gemini; West Saturn; West Tellus | Flagged red - not done by subsea or electrical department | Testing | General
0900-UP0133 | 12M SHEAR RAMS ROV INTERVENTION FUNCTION TEST - SUBSEA | 8 | Sonangol Libongos; West Carina; West Gemini; West Polaris; West Saturn; West Tellus; West Vela | Flagged red - not done by subsea or electrical department | Testing | General
0900-UB80091 | 90D HP SHEAR RAM FUNCTION TEST | 7 | Sonangol Quenguela; West Auriga; West Gemini; West Jupiter; West Polaris; West Saturn | Flagged red - not done by subsea or electrical department | Testing | General
0900-UB80092 | INITIAL BOP SUBSEA FUNCTION TEST | 7 | Sonangol Libongos; Sonangol Quenguela; West Jupiter; West Neptune; West Polaris; West Tellus; West Vela | Flagged red - not done by subsea or electrical department | Testing | BOP
0900-BT0201 | BWM INITIAL SUBSEA EMERGENCY ACCUMULATOR DRAWDOWN TEST | 5 | West Jupiter; West Neptune; West Polaris; West Tellus; West Vela | Flagged red - not done by subsea or electrical department | Testing | Accumulators
0900-BT0203 | 6M ACCUMULATOR DRAWDOWN TEST - SUBSEA | 5 | Sonangol Quenguela; West Neptune; West Polaris; West Tellus; West Vela | Flagged red - not done by subsea or electrical department | Testing | Accumulators
0900-BE0201 | DIVERTER 21 DAY SYSTEM FUNCTION TEST | 4 | West Auriga; West Capella; West Gemini; West Tellus | Flagged red - not done by subsea or electrical department | Testing | Diverter
0900-UB0226 | 6M ACOUSTIC CONTROL SYST. FUNCTION TEST - SUBSEA | 4 | Sonangol Quenguela; West Gemini; West Polaris; West Tellus | Flagged red - not done by subsea or electrical department | Testing | General
0900-UB0228 | 60M EMERGENCY SYSTEM SUBSEA TEST | 4 | Sevan Louisiana; Sonangol Quenguela; West Gemini | Flagged red - not done by subsea or electrical department | Testing | General
0900-BT0202 | 6M EMERGENCY ACCUMULATOR DRAWDOWN TEST - SUBSEA | 3 | Sonangol Quenguela; West Polaris; West Vela | Flagged red - not done by subsea or electrical department | Testing | Accumulators